## Work Plan
WORK PLAN FOR CONSERVATION AGREEMENTS IN THE SATHYAMANGALAM TIGER RESERVE (2017-19) KEYSTONE FOUNDATION
Activity | Specific Project Phase | Sub-activities | Output | Target | Product/deliverables | When | [7 empty] | Who
[6 empty] | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8
Phase 1: Community Engagement
Community engagement meetings | Engagement | Organize 12 community engagement meetings | Communities understand conservation agreements | 12 meetings (2 per hamlet) | Meeting minutes | [8 empty] | Keystone and APPCL | bar: When Q1 to When Q2
Partners/stakeholders engagement | Engagement | Organize 4 partner/stakerholder engagement meetings | Partners / stakeholders understand CA | 4 meetings - targeting APPCL, Forest Department, Eco-development Committees/Village Forest Committees, Local Panchayat members/leaders, traders, Farmer Co-operative Societies, WWF etc. | Meeting minutes | [8 empty] | Keystone | bar: When Q1 to When Q2
Staff and partners training on CAs | Engagement | Organize 2 days trainings on CAs | Staff and partners understand CA | 2 trainings | Training report | [8 empty] | Keystone | bar: When Q1
Phase 2 : Design and Negotiation
Design and negotiate CAs with community | Developing CA | CAs designed and negotiated and shared with CSP for peer review | Draft CAs | 6 draft CAs | Draft CAs | [8 empty] | Community members, Keystone, APPCL, CSP, other partners | bar: When Q1
Sign CAs | CA agreed and signed | CA signed with communities | Signed CAs | 6 CAs | 6 signed CAs | [8 empty] | Community, Keystone, APPCL, Forest departmen t other partners | bar: When Q1
Phase 3: Implementation
Preparation and training on monitoring protocols | Implementation and Monitoring | Organize 3 trainings | Monitoring protocols established and training of barefoot ecologists | 3 trainings | Monitoring protocol, Training reports | [8 empty] | Keystone, APPCL, other partners | bar: When Q1
Promote sustainable NTFP harvesting (Priority 1) | Implementation | Develop/review and adopt NTFP harvesting protocol | 1 NTFP harvesting protocol adopted by community | Protocol developed and adopted | 1 protocol on NTFP harvest | [8 empty] | Community, Keystone, APPCL | bar: When Q3
| Implementation | Training on NTFP harvesting protocol | Community understand the harvesting protocols | 6 trainings (1 per hamlet) | Training reports | [8 empty] | Community, Keystone, APPCL | bar: When Q3
| Implementation and Monitoring | Implementation and monitoring of NTFP harvesting protocol | NTFP protocol monitoring plan | Monitoring plans developed; data collection and analysis | Monitoring data | [8 empty] | Community(barefoot ecologists), Keystone, APPCL
| Implementation | Setting up local procurment centre for NTFPs and training on storage and handling of NTFPs | Procurement centres for NTFPs and better handling of NTFPs | 4 procurement centres | 4 procurement centres | [8 empty] | Keystone, APPCL, Community | bar: When Q5; When Q7
| Review | Review |  | 3 reviews | Review meeting reports | [8 empty] | Community, Keystone, APPCL | bar: When Q3; When Q6; When Q8
| Implementation | Linkages to market access and branding of NTFP products | NTFP products branded and accessing narkets |  | volumes accessing markets | [8 empty] | APPCL, Keystone | bar: When Q5 to When Q8
| Implementation | Initiate actions for certification for selected NTFP species | Two NTFPs certified LFE | 2 NTFPs certified | Certification | [8 empty] | Keystone, APPCL, LFE | bar: When Q7 to When Q8
| Monitoring and Training | Crafts training and market linkages | Craft products accessing markets through APPCL | 2 crafts products accessing markets | Training reports and crafts developed and marketed through APPCL | [8 empty] | Keystone | bar: When Q3 to When Q4; When Q8
Promote organic agriculture (Priority 2) | Monitoring and Training | Training on Participatory Guarantee Systems (PGS) for organic agriculture to include bio inputs | Understanding and practice of PGS | 12 trainings (2 per hamlet) | Training reports | [8 empty] | Keystone | bar: When Q2
| Implementation and Monitoring | Implementation and monitoring of PGS guidelines | PGS practices adopted by the community | 6 hamlets | Maps of land under PGS certification process | [8 empty] | Community(barefoot ecologists), Keystone, APPCL
| Implementation | Bio input store | Communities purchase bio-inputs from the store | 50% of farmers use the bio input store | Bio-input store set up | [8 empty] | Keystone | bar: When Q2
| Implementation | Linkages to APPCL | Buy back arrangements by APPCL for farm produce | 40% of farm produce procurred by APPLC | Procurement reports and sales report from APPCL | [8 empty] | APPCL | bar: When Q4 to When Q8
| Monitoring | Water bodies conservation measures and monitoring | Water bodies conserved | 30% of water bodies conserved | Location maps of water bodies and reports of interventions made. | [8 empty] | Keystone | bar: When Q3 to When Q8
| Implementation and Monitoring | To explore crop protection measures through monitoring and relevant trainings | Data on extent of crop damage and crop protection measures established | 20% of farms covered | Reports on crop damages; trainings and suggested measures to prevent crop damage | [8 empty] | Keystone and other agencies (to be identified) | bar: When Q3 to When Q8
| Review | Review |  | 3 reviews | Review meeting reports | [8 empty] | Community, Keystone, APPCL | bar: When Q3; When Q6; When Q8
Habitat improvement (Priority 3) | Monitoring | Baseline survey of fuel wood dependence and collection zones in the region | Understanding of the fuelwood requirements | 6 hamlets | Fuel wood status report and maps for each hamlet | [8 empty] | Keystone | bar: When Q1 to When Q2
| Implementation | Development and adoption of fuelwood collection guidelines | Fuelwood guidelines developed and adopted | 1 guideline protocol | guideline prototo | [8 empty] | Communities and Keystone | bar: When Q2
| Implementation and Monitoring | Implementation and monitoring of fuel wood collection guidelines | Communites adopt fuelwood collection guidelines | 6 hamlets | Monitoring data | [8 empty] | Community(barefoot ecologists), Keystone | bar: When Q3 to When Q8
| Implementation | introduction/distribution of ecostoves to compliant households | Communities use fuel efficient stoves and lantana for fuel | 6 hamlets | 50% of households adopt fuel efficient stoves | [8 empty] | Keystone, APPCL | bar: When Q5; When Q7
| Implementation | Nursery for fuel wood and native species | Enterprise model through nurseries | 6 nurseries (one in each hamlet) | Nurseries set up and land allocated for raising of fuel wood and native species | [8 empty] | Keystone | bar: When Q4 to When Q8
| Review | Review |  | 3 reviews | Review meeting reports | [8 empty] | Community, Keystone,APPCL | bar: When Q3; When Q6; When Q8
Improved animal husbandary practices (Priority 4) | Monitoring | Baseline survey of livestock and existing animal husbandry practices in the region | Understanding of the dependance on forests for livestock grazing | 6 hamlets | Baseline report on animal husbandry practices and maps | [8 empty] | Keystone | bar: When Q1 to When Q2
| Implementation and Monitoring | Grazing plans developed, implemented and monitored | Communities adhere to the grazing plan | 6 hamlets | Grazing plans for 6 hamlets and monitoring data | [8 empty] | Community(barefoot ecologists), Keystone | bar: When Q2 to When Q8
| Implementation | Training of para vets and herders | Communities trained on veterinary practices | 10 para vets - 2 trainings | Training reports | [8 empty] | Other identified partners | bar: When Q3; When Q6
| Implementation | Creation of fodder banks/cultivation/sale of manure | Communities depend on the fodder bank and willingness to cultivate fodder species | 6 fodder banks | Fodder banks set up | [8 empty] | Keystone, Community | bar: When Q5 to When Q8
| Implementation | Creation of village compensation fund for livestock loss | Communities contribute to the village fund | 6 village funds | Protocols for village fund functioning | [8 empty] | Keystone, Community | bar: When Q7 to When Q8
| Review | Review |  | 3 reviews | Review meeting reports | [8 empty] | Community, Keystone | bar: When Q3; When Q6; When Q8
Phase 4: Monitoring and evaluation
Develop a monitoring plan | Monitoring | Develop CA monitoring plan for all activities | Monitoring plan/protocols established | Monitoring plans for 6 CA s | 6 monitoring plans | [8 empty] | Keystone, APPCL, Community | bar: When Q1
| Monitoring | Monitoring of all CA s | Understanding of the progress and implementation of CA s by the community | 6 CA s | Data and progress reports | [8 empty] | Keystone, APPCL, Community | bar: When Q1
| Monitoring | Setting up of permanent plots for habitat quality monitoring | Permanent plots established | 6 permanent plots | Monitoring data and reports | [8 empty] | Community(barefoot ecologists), Keystone
Evaluation | Evaluation | Mid term evaluation of the project | Evaluating the impacts of the project | 1 evaluation report | Evaluation Report | [8 empty] | External agency | bar: When Q4
Partnership and Scaling up
Adoption of CA model by external partners | Partnerships | Outreach events and meetings with partners for CA model replication | CA signed by external partner and community | at least 2 partners adopting CA model | Signed CA | [8 empty] | APPCL, LFE, other agencies (to be identified) | bar: When Q1; When Q7
Program Management
| Program evaluation and results | Quarterly reporting | Reports on the progress of CAs, monitoring and tranining as per CI project progress reporting | 7 quarterly reports | Reports | [8 empty] | Keystone | bar: When Q2 to When Q8
| Program evaluation and results | End of project report |  | Report | Final Program report | [8 empty] | Keystone | bar: When Q8
| Program evaluation and results | Communication materials | Blog stories and photos, Communities feedback | 1 blog per year and regular photos | Regular Photo stories and blogs for CI | [8 empty] | Keystone